## AIPM
Project | Summary | Issue Type | Epic Link | Labels | Estimate (Hours) | Assignees
AIPM | Establish the foundation for the predictive maintenance system. | Epic | - | Preparation and Planning | -
AIPM | Conduct a needs assessment and feasibility study. | New Feature | Establish the foundation for the predictive maintenance system. | Preparation and Planning | 120 | Business Analyst, Data Scientist, AI Strategist
AIPM | Select critical equipment for initial implementation. | New Feature | Establish the foundation for the predictive maintenance system. | Preparation and Planning | 60 | Operations Manager, AI Engineer, Maintenance Manager
AIPM | Assemble a cross-functional project team. | New Feature | Establish the foundation for the predictive maintenance system. | Preparation and Planning | 40 | HR Manager, Project Manager, AI Project Manager
AIPM | Develop a project charter, defining scope, objectives, and KPIs. | New Feature | Establish the foundation for the predictive maintenance system. | Preparation and Planning | 80 | Project Manager, Business Analyst, Stakeholders
AIPM | Choose the appropriate technologies and conduct pilot testing on selected equipment. | Epic | - | Technology Selection | - | -
AIPM | Evaluate and select IoT sensors, cloud platforms, and AI technologies. | New Feature | Choose the appropriate technologies and conduct pilot testing on selected equipment. | Technology Selection | 100 | AI Engineer, IoT Specialist, Cloud Solutions Architect
AIPM | Deploy IoT sensors on selected machinery and integrate data collection mechanisms. | New Feature | Choose the appropriate technologies and conduct pilot testing on selected equipment. | Technology Selection | 90 | IoT Specialist, Field Engineer, Integration Specialist
AIPM | Develop initial AI models for anomaly detection and failure prediction. | New Feature | Choose the appropriate technologies and conduct pilot testing on selected equipment. | Technology Selection | 160 | Data Scientist, AI Engineer, Machine Learning Specialist
AIPM | Conduct pilot testing to assess the effectiveness of predictive maintenance models. | New Feature | Choose the appropriate technologies and conduct pilot testing on selected equipment. | Technology Selection | 120 | QA Analyst, AI Engineer, Operations Manager
AIPM | Collect feedback and refine AI models based on pilot results. | New Feature | Choose the appropriate technologies and conduct pilot testing on selected equipment. | Technology Selection | 80 | Data Scientist, AI Engineer, End Users
AIPM | Develop the full predictive maintenance system and integrate it with existing systems. | Epic | - | System Development & Integration | - | -
AIPM | Enhance AI models for improved accuracy and reliability. | New Feature | Develop the full predictive maintenance system and integrate it with existing systems. | System Development & Integration | 140 | AI Engineer, Data Scientist, Machine Learning Specialist
AIPM | Develop the user interface (dashboard) for real-time monitoring and alerts | New Feature | Develop the full predictive maintenance system and integrate it with existing systems. | System Development & Integration | 100 | UI/UX Designer, Front-end Developer, Data Analyst
AIPM | Integrate predictive maintenance system with existing ERP/CMMS systems for streamlined workflow. | New Feature | Develop the full predictive maintenance system and integrate it with existing systems. | System Development & Integration | 110 | Integration Specialist, System Administrator, ERP Consultant
AIPM | Implement security protocols to ensure data privacy and integrity. | New Feature | Develop the full predictive maintenance system and integrate it with existing systems. | System Development & Integration | 70 | Cybersecurity Specialist, Data Privacy Officer, Network Engineer
AIPM | Deploy the predictive maintenance system across all targeted equipment and facilities. | Epic | - | Full-Scale Deployment | - | -
AIPM | Scale up the deployment of IoT sensors across all critical machinery | New Feature | Deploy the predictive maintenance system across all targeted equipment and facilities. | Full-Scale Deployment | 100 | IoT Specialist, Field Engineer, Project Coordinator
AIPM | Roll out the predictive maintenance system to all relevant stakeholders. | New Feature | Deploy the predictive maintenance system across all targeted equipment and facilities. | Full-Scale Deployment | 90 | Project Manager, AI Project Manager, Training Coordinator
AIPM | Conduct comprehensive training sessions for maintenance teams and other end-users. | New Feature | Deploy the predictive maintenance system across all targeted equipment and facilities. | Full-Scale Deployment | 120 | Training Coordinator, Technical Trainer, Maintenance Manager
AIPM | Establish a support and maintenance framework for the predictive maintenance system. | New Feature | Deploy the predictive maintenance system across all targeted equipment and facilities. | Full-Scale Deployment | 80 | Support Manager, Maintenance Engineer, IT Support Specialist
AIPM | Monitor the system's performance, evaluate its impact, and implement continuous improvements. | Epic | - | Monitoring, Evaluation, and Continuous Improvement | - | -
AIPM | Monitor system performance and collect data on key metrics such as reduced downtime and maintenance savings. | New Feature | Monitor the system's performance, evaluate its impact, and implement continuous improvements. | Monitoring, Evaluation, and Continuous Improvement | 60 | Data Analyst, Operations Manager, AI Engineer
AIPM | Conduct regular review meetings to evaluate the system against initial KPIs and objectives. | New Feature | Monitor the system's performance, evaluate its impact, and implement continuous improvements. | Monitoring, Evaluation, and Continuous Improvement | 50 | Project Manager, Quality Assurance Manager, Data Scientist
AIPM | Gather user feedback for identifying areas of improvement. | New Feature | Monitor the system's performance, evaluate its impact, and implement continuous improvements. | Monitoring, Evaluation, and Continuous Improvement | 40 | User Experience Researcher, AI Engineer, Feedback Coordinator
AIPM | Implement updates and enhancements to the predictive maintenance models and user interface based on feedback and evolving needs. | New Feature | Monitor the system's performance, evaluate its impact, and implement continuous improvements. | Monitoring, Evaluation, and Continuous Improvement | 100 | Front-end Developer, AI Engineer, Data Scientist
AIPM | Expand the predictive maintenance solution to additional machinery, facilities, or business units. | Epic | - | Expansion and Scaling | - | -
AIPM | Identify additional equipment and facilities for implementation. | New Feature | Expand the predictive maintenance solution to additional machinery, facilities, or business units. | Expansion and Scaling | 60 | Operations Manager, AI Strategist, Project Coordinator
AIPM | Assess the need for further customization or development of AI models for new types of machinery. | New Feature | Expand the predictive maintenance solution to additional machinery, facilities, or business units. | Expansion and Scaling | 120 | AI Engineer, Machine Learning Specialist, Data Analyst
AIPM | Scale the predictive maintenance system to cover the newly identified areas. | New Feature | Expand the predictive maintenance solution to additional machinery, facilities, or business units. | Expansion and Scaling | 80 | Project Manager, Systems Engineer, IoT Specialist
AIPM | Evaluate the system's scalability and adapt the infrastructure as necessary to support expanded operations. | New Feature | Expand the predictive maintenance solution to additional machinery, facilities, or business units. | Expansion and Scaling | 70 | Cloud Solutions Architect, Network Engineer, AI Project Manager
2240
896000
56